## Test Scenarios
Project Name | Forum Buddy
Client | Zealous Tech Corp
Reference Document | FRS
Created By | Razak Mohamed S
Creation Date | 2021-12-31
Approval Date | 2021-12-31
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 | FRS | Validate the working of Login functionality | P0 | 10
TS_002 | FRS | Validate the working of Logout functionality | P0 | 4
TS_003 | FRS | Validate the working of Home Page functionality | P0 | 13
TS_004 | FRS | Validate the working of Adding New Forum | P1 | 18
TS_005 | FRS | Validate the working of Navigation functionality | P1 | 10
TS_006 | FRS | Validate the working of Listing available forums functionality | P1 | 5
TS_007 | FRS | Validate the working of EDIT forum functionality | P2 | 20
TS_008 | FRS | Validate the working of Delete forum functionality | P2 | 5
TS_009 | FRS | Validate the working of Secutity functionality | P1 | 20
TS_010 | FRS | Validating the brand of Site | P3 | 2
TS_011 | FRS | Validating UI | P3 | 10
Modules
LOGIN
LOGOUT
ADD FORUM
LIST FORUM
EDIT
DELETE

## RTM
Project Name | ForumBuddy
Client | Zealous Tech Corp
Reference Document | FRS
Created By | Razak Mohamed S
Creation Date | 2022-01-03
Approval Date | DD-MM-YYYY
Requirement ID | Test Scenario ID | Test Scenario Description | Tes Case ID'S
1.1 | TS_001 | Validate the working of Login functionality | TC_LF_001 TC_LF_002 TC_LF_003 TC_LF_004 TC_LF_005 TC_LF_006 TC_LF_007 TC_LF_008 TC_LF_009 TC_LF_010
1.2 | TS_003 | Validate the working of Home Page functionality | TC_HP_001 TC_HP_002 TC_HP_003 TC_HP_004 TC_HP_005 TC_HP_006 TC_HP_007 TC_HP_008 TC_HP_009 TC_HP_010 TC_HP_011 TC_HP_012 TC_HP_013
1.3 | TS_002 | Validate the working of Logout functionality | TC_LO_001 TC_LO_002 TC_LO_003 TC_LO_004

## Environment Setup
Project Name | ForumBuddy
Client | Zealous Tech Corp
Reference Document | FRS
Created By | Razak Mohamed S
Creation Date | 2022-01-03
Approval Date | DD-MM-YYYY
War File | ForumBuddy
Webserver | Apache Tomcat | 32-bit/64-bit Windows Service Installer (pgp, sha512), from https://tomcat.apache.org/download-90.cgi
Database | XAMPP>> MySQL | https://www.apachefriends.org/download.html
Steps to execute | 1 | Install Apache tomcat
| 2 | Install XAMPP tool
| 3 | Open XAMPP Control panel
| 4 | Start tomcat and mysql servers
| 5 | Visit browser and type 'localhost'
| 6 | Click PHPMyAdmin link
| 7 | Click 'new' link to create database 'deepa'
| 8 | copy and paste WAR file to webapps folder in apache software foundation at C:\Programfiles
| 9 | visit bin folder of apache software foundation
| 10 | start by click the tomcat.exe file inorder to start apache to host WAR file

## Login
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_LF_001 | (TS_001) Login Functionality | Validate logging into the Application using valid credentials | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser 2. Login credentials for an existing account are required | 1. Click on 'Login' option 2. Enter the valid user name 3. Enter the respective password 4. Click on Login button | Username: deepa Password: deepaforum | 1.User should be navigated to Login page 2.User should get logged in and taken to the 'Home' page | 1.User has navigated to Login page 2. User Logged in with TD-1 and Home page verified | P0 | PASS | Verified
TC_LF_002 | (TS_001) Login Functionality | Validate logging into the Application using invalid credentials (i.e. Invalid username and Invalid Password) | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser 2. Login credentials for an existing account are required | 1. Click on 'Login' option 2. Enter the valid user name 3. Enter the respective password 4. Click on Login button | Username: deepas Password: dipaforum | 1.Ensure url should be passed like below http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT/login 2. Should have same login page | 1. URL Has verified that it has authenticating TD-1 2. Login page again viewd after TD-1 Executed | P0 | PASS | Verified
TC_LF_003 | (TS_001) Login Functionality | Validate logging into the Application using invalid username and valid Password | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser 2. Login credentials for an existing account are required | 1. Click on 'Login' option 2. Enter the valid user name 3. Enter the respective password 4. Click on Login button | Username: razzak Password: deepaforum | 1.Ensure url should be passed like below http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT/login 2. Should have same login page | 1. URL Has verified that it has authenticating TD-1 2. Login page again viewd after TD-1 Executed | P0 | PASS
TC_LF_004 | (TS_001) Login Functionality | Validate logging into the Application using valid username and invalid Password | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser 2. Login credentials for an existing account are required | 1. Click on 'Login' option 2. Enter the valid user name 3. Enter the respective password 4. Click on Login button | Username: razak Password: depaforum | 1.Ensure url should be passed like below http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT/login 2. Should have same login page | 1. URL Has verified that it has authenticating TD-1 2. Login page again viewd after TD-1 Executed | P0 | PASS
TC_LF_005 | (TS_001) Login Functionality | Validate logging into the Application without providing any credentials | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser 2. Login credentials for an existing account are required | 1. Click on 'Login' option 2. Click on Login button | Not Applicable | 1.Ensure url should be passed like below http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT/login 2. Should have same login page | 1. URL Has verified that it has authenticating TD-1 2. Login page again viewd after TD-1 Executed | P0 | PASS
TC_LF_006 | (TS_001) Login Functionality | Validate logging into the Application using Keyboard keys (Tab and Enter) | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser 2. Login credentials for an existing account are required | 1. Click on 'Login' option 2. Enter the valid user name 3. press TAB to move password 4. Enter the respective password 5. Press TAB to move LOGIN button 6. Enter LOGIN | Username: razak Password: deepaforum | 1. Tabs and Enter functionalities should visit components 2. User should be able to log into the application | 1. Tabs and Enter keys are verified 2. which able to login by TD-1 | P0 | PASS
TC_LF_007 | (TS_001) Login Functionality | Validate username and Password text fields in the Login page have the place holder text | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser 2. Login credentials for an existing account are required | 1. Click on 'Login' option 2. Expected Result -1 | Not Applicable | 1. Proper place holder text should be displayed inside the 'username' and 'Password' text fields | 1. Placeholder's in username and password fields are verified | P1 | PASS
TC_LF_008 | (TS_002) Login Functionality | Validate the Password is not visible in the Page Source | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser 2. Login credentials for an existing account are required | 1. Click on 'Login' option 2. Enter the valid user name 3. Enter the respective password 4. Click on Login button | Not Applicable | 1. Password text should not be visible in the Page source | 1. Password text visibility verified | P1 | PASS
TC_LF_009 | (TS_001) Login Functionality | Validate Logging into the Application, closing the Browser without loggingout and opening the application in the Browser again | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser 2. Login credentials for an existing account are required | 1. Click on 'Login' option 2. Enter the valid user name 3. Enter the respective password 4. Click on Login button 5. Home page 6. Close Browser without logout | Username: razak Password: deepaforum | 1. Loggedin Sesion should be logged out after reopen | 1. ER-1 failed | P0 | FAIL | Forum Buddy_BUG_001
TC_LF_010 | (TS_001) Login Functionality | Validate user is able to navigate to Login page dispite of visiting an athorised page directly | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser | 1. Append the 'new' or any keyword end of URL | Not Applicable | 1. User should be navigate to LOGIN page | 1. Unauthorised page visiting has verified | P0 | PASS

## Home
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_HP_001 | (TS_003) Home Page | Validate navigating to Home Page from login page | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser 2. Login credentials for an existing account are required | 1. Login with Given TD-1 from login page 2. Successful login expect ER-1 | username: razak password: deepaforum | 1. User should be taken to Home page | 1. User Logged in with TD-1 and Home page verified | P0 | PASS
TC_HP_002 | (TS_003) Home Page | Validate the logged person name navigating to Home Page from login page | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser 2. Login credentials for an existing account are required | 1. Login with Given TD-1 from login page 2. Successful login expect ER-1 and ER-2 | username: deepa password: deepaforum | 1. User should be taken to Home page 2. logged person deepa should be visible in home page | 1. User Logged in with TD-1 and Home page verified | P0 | PASS
TC_HP_003 | (TS_003) Home Page | Validate the logged person name navigating to Home Page from login page | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser 2. Login credentials for an existing account are required | 1. Login with Given TD-1 from login page 2. Successful login expect ER-1 and ER-2 | username: razak password: deepaforum | 1. User should be taken to Home page 2. logged person razak should be visible in home page | 1. User Logged and taken to Home page with TD-1 2. Logged person 'razak' has shown in green color | P0 | PASS
TC_HP_004 | (TS_003) Home Page | Validate navigating to Home page from any page of the Applcation using Logo | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser | 1. Click on the Logo 'Deepa Forum' in our application (Validate ER-1) | Not Applicable | 1. User should be taken to Home page | 1. From any page to home through logo is not navigated | P1 | FAIL | Forum Buddy_BUG_002
TC_HP_005 | (TS_003) Home Page | Validate navigating to Home page from any page of the Applcation using 'ShowAll' link | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser | 1. Click on the button 'ShowAll' in our application (Validate ER-1) | Not Applicable | 1. User should be taken to Home page | Home page arrives when ever ShowAll clicked from any page has verified | P1 | PASS
TC_HP_006 | (TS_003) Home Page | Validate all available forums should be displayed in the Home Page | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser | 1. Click on the ''ShowAll" link and verify ER-1 and ER-2 | Not Applicable | 1. Should display the table consists of Headers 2. Should display the forum information of respective headers if forum's available in database | 1. Tables headers caqme up with Forum Properties 2. All forum Information verified with database | P1 | PASS
TC_HP_007 | (TS_003) Home Page | Validate Link which navigate to edit forum page by clicking from each forum id in our home page | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser | 1. Click on the edit with yellow link of forum id and expect the result ER-1, ER-2, ER-3 | Not Applicable | 1. Verify that atleast one forum data should be displayed 2. Make sure Forum id is shown 3. By clicking it verify navigating to Edit page with respective forum data | 1. Forum data are verified 2. Forum id's available forum's are shown 3. Edit page navigation verified with reswpective forum data | P1 | PASS
TC_HP_008 | (TS_003) Home Page | Validate Red colour Erase button leads you showing new available forum by deleting the one | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser | 1. Click on the Erase button and verify ER-1, ER-2, ER-3 and ER-4 | Not Applicable | 1. Verify that atleast one forum data available in the table 2. Make sure Erase button is available at end of each forum row's Action Column 3. Verify the URL should look like "http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT/del/" with deleted forum id 4. Ensure Home page displayed again with Table | 1. Forum data availability verified 2. ERASE button verified 3. URL with deleted forum id verified 4. Verification of home after deletion done | P1 | PASS
TC_HP_009 | (TS_003) Home Page | Validate the UI of 'Home' page functionality | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser | 1. Check the UI of the functionality related to 'Home' page (Validate ER-1) | Not Applicable | 1. Proper UI adhering to the UI checklist should be displayed for the 'Home' page functionality | UI Functionality test has verified successfully | P2 | PASS
TC_HP_010 | (TS_003) Home Page | Validate the 'Home' page functionality in all the supported environments | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser | 1. Check the 'Home' page functionality in all the supported environments (Validate ER-1) | Not Applicable | 1. 'Home' page functionality should work correctly in all the supported environments | Home navigation verified in all supported environments | P2 | PASS
TC_HP_011 | (TS_003) Home Page | Validate the 'Home' page functionality after logout | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser | 1. Visit Home page 2. Click on the 'Logout' button verify ER-1 3. Click back and verify ER-2, ER-3 | Not Applicable | 1. Verify Login page displayed 2. Verify Home page is displayed 3. Verify Multiple times back pressed | 1. Login verified 2. Home page verified 3. After logout and clicked back multiple times home page not shown | P0 | PASS
TC_HP_012 | (TS_003) Home Page | Validate the 'Home' page functionality by Displaying deleted Forum name | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser | 1. Click on the Erase button and verify ER-1, ER-2 and ER-3 | Not Applicable | 1. Verify that atleast one forum data available in the table 2. Ensure Home page displayed again with Table 3. Verify deleted forum name in Home page | 1. Forum Data verified 2. Erase button clicked and deletion performed 3. After deletion deleted forum name verified | P1 | PASS
TC_HP_013 | (TS_003) Home Page | Validate the 'Home' page functionality by Displaying edited Forum name | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser | 1. Click on the link of forum id verify ER-1, ER-2 and ER-3 | Not Applicable | 1. Ensure ateast we have one Forum information 2. Link of Edit in Forum id enables, also direct us to edit page with data, change accordingly 3. Verify home page is displayed with Updated forum name | 1. Forum Data verified 2. Link of edit page verified 3. After change updated forum name verified | P1 | PASS

## Logout
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_LO_001 | (TS_002) Home Page | Validating Login page after logout clicked | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser | 1. Click on logout and verify ER-1 | NA | 1. Should direct us to 'login' page
TC_LO_002 | (TS_002) Home Page | Validating logout functionality from home page | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser | 1. Click on logout and verify ER-1, ER-2 | NA | 1. Should direct us to 'login' page 2. Back should not direct us to home page again
TC_LO_003 | (TS_002) Home Page | Validating logout functionality from add page | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser | 1. Click on logout and verify ER-1, ER-2, ER-3 | NA | 1. Should direct us to 'login' page 2. Back should not direct us to add page again 3. Nothing should impact if you would have entered details in adding page before Approve clicked
TC_LO_004 | (TS_002) Home Page | Validating logout functionality from edit page | 1. Open the Application URL (https://http://localhost:8080/DeepaSpringBoot-0.0.1-SNAPSHOT) in any supported Browser 2. Logged with authorised user TD-1 | 1. Log in With TD-1 2. Click on Forum id link and ensure ER-1, ER-2, ER-3 3. After logout verify ER-4 | Username: deepa password: deepaforum | 1. Ensure Edit page is displayed after link has clicked from forum id 2. Edit page should contain respective forum data with enable to change 3. After logout no update should happen 4. Should display login page again